## Sheet1
Date | Work related to project
Week 1
2022-03-28 | Initial meeting with project group
2022-03-29
2022-03-30 | Brought home the robot, identified and studied the datasheets of the components
2022-03-31 | Meeting with the group, discussed work-structure and how to divide responsibilities
Found and shared an existing libray for Makeblock products. Many functions can be used for control of the robot.
2022-04-01 | Bought adapter for micro-USB to USB-A as well as a SD-card reader. Both intended for use with the raspberry pi zero w.
2022-04-02 | Built the robot.
Wrote code for the functionality that makes the robot move autonomously inside a limited area. The area was limited by black tape which the robot is instructed to avoid. Also made the robot turn if it encountered an obstacle. Additionally, wrote code to gather data from the built in gyroscope on the robot. This could be used for the directional information that need to be sent to the backend.
Conducted practical tests that confirmed that the code worked as intended.
2022-04-03 | Investigated different functions in the Makeblock library, specifically functions that make the engines turn a specified amount of degrees. This could be used to define the robots speed.
Week 2
2022-04-04 | Meeting with the other members working with the hardware. Discussed our dependencies and how to tackle the different requirements of the project. Also demonstrated the code I had written and the autonomous movements of the robot.
2022-04-05 | Meeting with the entire project team. Presented our dependencies and discussed how to prioritize work going forward. Brief walkthrough of how we should be using version control.
2022-04-06 | Setup automatic Wi-fi connection from rpi to mobile hotspot on boot as well as giving the rpi a static ip-address making ssh connection super easy.
Confirmed serial communication through USB between rpi and arduino Mega 2560. A simple python script on the rpi receiving and validating messages sent from the arduino.
2022-04-07 | Confirmed the camera functioning together with the rpi. Combined the code for the camera with the previous code testing serial communication. Now, when the robot detects a obstacle it sends a flag to the rpi which captures and saves a picture.
2022-04-08 | Standup followed by a short meeting with the other people in the hardware group, discussed the upcoming week.
2022-04-09 | Experimented with the speed of the robot, no clear results. At current config the bot moves at about 0.254m/s. It is not moving in a straight line though, maybe something that could be fixed with the help of the gyroscope in the future?
Updated the code for the rpi, creates a separate thread where the positional calculations are made whilst the main thread awaits serial input from the arduino regarding its current state. Edited arduino code to send updates regarding its state to the rpi over the serial communications. Arduino also awaits a acknowledgemen-message before continuing to make sure everything is properly synched. Also made a new proposal for the state-machine controling auto-drive.
2022-04-10
Week 3
2022-04-11 | Meeting with the hardware-group. Discussed our plans for the week and spoke about how to implement the bluetooth functionality in the arduino.
2022-04-12 | Studied the schematics of the Arduino Mega 2560 that the MeAuriga we have is based on. Noticed that the USB and Bluetooth share Tx and Rx which means that we will have to use the raspberry for Bluetooth. Notified the team about this in Discord and we had a meeting regarding this matter. Me and Eddie will meet up tomorrow and work with the Raspberry.
2022-04-13 | Met up with Eddie and configured the Raspberry to make connection possible. Wrote a simple python-script that could read and send serial data between the connection. Had a discussion with members of another team regarding the speed of the serial connection, they had experienced slow speeds at times, something to look out for.
2022-04-14
2022-04-15
2022-04-16
2022-04-17 | Studied ways of speeding up serial communication. One possible simple solution could be to increase the baudrate to 115200 bits/sec. Another could be to send as little data as possible each time, reducing the messages to just a few bits.
Week 4
2022-04-18
2022-04-19 | Meeting with the hardware-crew plus Dejan. Discussed how the communication between units (rpi, arduino, app) will work.
2022-04-20 | Short talk with Kiro reviewing and discussing the code he had written. Followed by a Stand-up meeting with the entire group.
2022-04-21 | Discussed positioning with Kiro. Explained how my solution worked.
2022-04-22 | Brief meeting with the hardware-crew regarding what we had done during the week. Reviewed Eddies code and showed everyone how we should work with branches and pullrequests.
2022-04-23
2022-04-24
Week 5
2022-04-25 | Sprint-planning with the project group.
2022-04-26
2022-04-27 | Met with Eddie at school and tried out the bluetooth connection to the application. Did not work. Looked for other solutions, landed on a Bluetooth classic solution where a server socket is created on the rpi. Had a chat with Micke from the frontend, we will meet up tomorrow to further develop our bluetooth solution.
2022-04-28 | Met with Eddie and Micke in school. Had some tech-trouble with the rpi so installed a new raspianOS on a separate SD-card. Confirmed connection between their app and the rpi with Bluetooth classic.
2022-04-29 | Meeting with the entire group. Discussed what we should be doing going forward. Gave the Rpi to Kiro as he and a member of the front-end team wanted to work with it over the weekend.
2022-04-30 | I finished writing the code for the rpi-controls. It should now be able to receive messages from a bluetooth client socket and through that control the Robots state-machine as well as listening to the robots actions during autonomous driving. Also calculating the position when moving forward. Need to do some testing to make sure that it works as intended during next week.
2022-05-01
Week6
2022-05-02 | Sprint planning with the team, our goal will be to test all communications between app -> rpi <-> mower
2022-05-03
2022-05-04
2022-05-05 | Tested the communications together. Noticed that the gyroscope returned inaccurate values when turning. Solved this by updating its orientation continously as the mower is moving, not just when it has performed a turn. App did not establish a connection but the autonomous driving is performed correctly with comms between mower and rpi and its position is calculated. What remains is to send the data to the backend.
2022-05-06 | Meeting where we discussed what we had done during the week and some group-ethics. Khaleel is going to work on the bluetooth over the weekend on a separate rpi4. I supplied him with adequate code and setup for the rpi so that he can perform relevant testing on his own.
2022-05-07 | Had a chat with Khaleel regarding the bluetooth functionality. He was able to connect to the rpi but the data seemed weird. Proposed to try sending a char instead of int.
2022-05-08