## Sheet1
Date | Work related to project
Week 1
2022-03-28 | Initial meeting with project group
2022-03-29
2022-03-30 | Brought home the robot, identified and studied the datasheets of the components
2022-03-31 | Meeting with the group, discussed work-structure and how to divide responsibilities
Found and shared an existing libray for Makeblock products. Many functions can be used for control of the robot.
2022-04-01 | Bought adapter for micro-USB to USB-A as well as a SD-card reader. Both intended for use with the raspberry pi zero w.
2022-04-02 | Built the robot.
Wrote code for the functionality that makes the robot move autonomously inside a limited area. The area was limited by black tape which the robot is instructed to avoid. Also made the robot turn if it encountered an obstacle. Additionally, wrote code to gather data from the built in gyroscope on the robot. This could be used for the directional information that need to be sent to the backend.
Conducted practical tests that confirmed that the code worked as intended.
2022-04-03 | Investigated different functions in the Makeblock library, specifically functions that make the engines turn a specified amount of degrees. This could be used to define the robots speed.
Week 2
2022-04-04 | Meeting with the other members working with the hardware. Discussed our dependencies and how to tackle the different requirements of the project. Also demonstrated the code I had written and the autonomous movements of the robot.
2022-04-05 | Meeting with the entire project team. Presented our dependencies and discussed how to prioritize work going forward. Brief walkthrough of how we should be using version control.
2022-04-06 | Setup automatic Wi-fi connection from rpi to mobile hotspot on boot as well as giving the rpi a static ip-address making ssh connection super easy.
Confirmed serial communication through USB between rpi and arduino Mega 2560. A simple python script on the rpi receiving and validating messages sent from the arduino.
2022-04-07 | Confirmed the camera functioning together with the rpi. Combined the code for the camera with the previous code testing serial communication. Now, when the robot detects a obstacle it sends a flag to the rpi which captures and saves a picture.
2022-04-08 | Standup followed by a short meeting with the other people in the hardware group, discussed the upcoming week.
2022-04-09 | Experimented with the speed of the robot, no clear results. At current config the bot moves at about 0.254m/s. It is not moving in a straight line though, maybe something that could be fixed with the help of the gyroscope in the future?
Updated the code for the rpi, creates a separate thread where the positional calculations are made whilst the main thread awaits serial input from the arduino regarding its current state. Edited arduino code to send updates regarding its state to the rpi over the serial communications. Arduino also awaits a acknowledgemen-message before continuing to make sure everything is properly synched. Also made a new proposal for the state-machine controling auto-drive.
2022-04-10
Week 3
2022-04-11 | Meeting with the hardware-group. Discussed our plans for the week and spoke about how to implement the bluetooth functionality in the arduino.
2022-04-12 | Studied the schematics of the Arduino Mega 2560 that the MeAuriga we have is based on. Noticed that the USB and Bluetooth share Tx and Rx which means that we will have to use the raspberry for Bluetooth. Notified the team about this in Discord and we had a meeting regarding this matter. Me and Eddie will meet up tomorrow and work with the Raspberry.
2022-04-13 | Met up with Eddie and configured the Raspberry to make connection possible. Wrote a simple python-script that could read and send serial data between the connection. Had a discussion with members of another team regarding the speed of the serial connection, they had experienced slow speeds at times, something to look out for.
2022-04-14
2022-04-15
2022-04-16
2022-04-17 | Studied ways of speeding up serial communication. One possible simple solution could be to increase the baudrate to 115200 bits/sec. Another could be to send as little data as possible each time, reducing the messages to just a few bits.
Week 4
2022-04-18
2022-04-19
2022-04-20
2022-04-21
2022-04-22
2022-04-23
2022-04-24
Week 5
2022-04-25
2022-04-26
2022-04-27
2022-04-28
2022-04-29
2022-04-30
2022-05-01
Week6
2022-05-02
2022-05-03
2022-05-04
2022-05-05
2022-05-06
2022-05-07
2022-05-08