## Sheet1
Date | Work related to project
Week 1
2022-03-28 | Initial meeting with project group
2022-03-29
2022-03-30 | Brought home the robot, identified and studied the datasheets of the components
2022-03-31 | Meeting with the group, discussed work-structure and how to divide responsibilities
Found and shared an existing libray for Makeblock products. Many functions can be used for control of the robot.
2022-04-01 | Bought adapter for micro-USB to USB-A as well as a SD-card reader. Both intended for use with the raspberry pi zero w.
2022-04-02 | Built the robot.
Wrote code for the functionality that makes the robot move autonomously inside a limited area. The area was limited by black tape which the robot is instructed to avoid. Also made the robot turn if it encountered an obstacle. Additionally, wrote code to gather data from the built in gyroscope on the robot. This could be used for the directional information that need to be sent to the backend.
Conducted practical tests that confirmed that the code worked as intended.
2022-04-03 | Investigated different functions in the Makeblock library, specifically functions that make the engines turn a specified amount of degrees. This could be used to define the robots speed.
Week 2
2022-04-04 | Meeting with the other members working with the hardware. Discussed our dependencies and how to tackle the different requirements of the project. Also demonstrated the code I had written and the autonomous movements of the robot.
2022-04-05 | Meeting with the entire project team. Presented our dependencies and discussed how to prioritize work going forward. Brief walkthrough of how we should be using version control.
2022-04-06
2022-04-07
2022-04-08
2022-04-09
2022-04-10
Week 3
2022-04-11
2022-04-12
2022-04-13
2022-04-14
2022-04-15
2022-04-16
2022-04-17
Week 4
2022-04-18
2022-04-19
2022-04-20
2022-04-21
2022-04-22
2022-04-23
2022-04-24
Week 5
2022-04-25
2022-04-26
2022-04-27
2022-04-28
2022-04-29
2022-04-30
2022-05-01
Week6
2022-05-02
2022-05-03
2022-05-04
2022-05-05
2022-05-06
2022-05-07
2022-05-08